## Slide 1: Field trial plan

## Slide 2: Work plan
Phase 1 – Testing monitoring architecture
  Review of existing monitoring infrastructures
  Consultation with University of Nottingham ETC (http://www.nottingham.ac.uk/etc/) and Estates (http://www.nottingham.ac.uk/estate/) regarding current monitoring capabilities of University of Nottingham and local workplaces
  Acquiring suitable sensors and sensor hub (e.g. M2M module) – check compatibility/portability with China
  Deploying and testing sensor infrastructure in test site (Horizon Research)

## Slide 3: Work plan
Phase 2 – Testing data store for monitoring
  Developing schema for data store
  Deploying data store on suitable web platform
  Linking sensor infrastructure to data store and testing scalability of data store for long-term monitoring

## Slide 4: Work plan
Phase 3 – Prototype (monitoring) user interfaces
  Review of existing user interfaces for Carbon emission awareness
  Rapid iteration of prototypes based on paper prototyping and short test deployments at local sites (student halls of residence at University of Nottingham, Horizon Research)
  Internationalise interfaces

## Slide 5: Work plan
Phase 4 – Test control architecture
  Acquire and integrate suitable control hardware with monitoring hardware
  Modify data store to support control
  Test control functionality (reliability and response speed)

## Slide 6: Work plan
Phase 5 – Prototype enhanced UI3
  Modify UI3 to enable control functionality
  Rapid iteration of UI3 prototype in consultation with various potential end-users

## Slide 7: Work plan
Phase 6 – Formal field trials
  Determine observation/data capture method + sites
  Installation of monitoring/control infrastructure + UI devices on sites
  Pre-trial interviews/focus groups with users
  Trial
  Post-trial interviews/focus groups with users

## Slide 8: Work plan
Phase 7 - Analysis
  Data sessions/workshop with stakeholders
  Dissemination of results
  Plan for follow-on proposals

## Slide 9: Work plan
Phase | Months |  |  |  |  |  |  | 
 | 1-3 | 4-6 | 7-9 | 10-12 | 13-15 | 16-18 | 19-21 | 22-24
1 |  | Impl. monitoring |  |  |  |  |  | 
2 |  | Impl. data store |  |  |  |  |  | 
3 |  |  | Prototype UIs |  |  |  |  | 
4 |  |  |  | Impl. control |  |  |  | 
5 |  |  |  |  |  |  |  | 
6 |  |  |  |  |  | Field trial |  | 
7 |  |  |  |  |  |  | Analysis | 
Notes: 3 month app spec
1 month buy infrastructure
3 months get Irene’s data
4 months analyse Irene’s data
3 months spec the deployment in china/uk
6 Months personal container
3 months first paper prototypes